## Slide 1
PROGRESS REVIEW · MAY – SEPTEMBER 2026
Solar & Space Weather
Monitoring Dashboard
A common web interface for e-CALLISTO solar radio observations, H-alpha / solar imaging and multi-parameter space weather data.
G. L. S. S. Liyanage
Research Scientist · Space Applications Division
Arthur C. Clarke Institute for Modern Technologies
Supervisor: Mr. Saraj Gunasekera, Principal Research Scientist
Notes: Progress review of the assignment 'Spectropolarimetric Observations of Solar Radio Bursts using Log-Periodic Antenna and Long Wave Antenna Systems'. This presentation covers the software deliverables from May to September 2026 and the plan for October to December.

## Slide 2
ASSIGNMENT · MAY – DECEMBER 2026
Where we are on the plan
ACCIMT · Space Applications Division
2
Assignment: Spectropolarimetric observations of solar radio bursts using log-periodic and long-wave antenna systems. The software component is a modern acquisition, archiving, monitoring and visualisation platform for CALLISTO and space weather data.
May
Literature
review
Jun
Requirements &
architecture
Jul
Prototype web
interface
Aug
Common monitoring
dashboard
Sep
H-alpha & imaging
visualisation
Oct
Multi-parameter
integration
Nov
AI burst
classification
Dec
Full platform &
documentation
▲ we are here
18
dashboard pages
delivered
14
automated data
collectors
3
trained ML
burst models
5 / 8
monthly milestones
completed
Notes: Five of the eight monthly milestones are complete. The software platform is running end to end; October to December is integration, AI detection and documentation.

## Slide 3
HOW IT IS BUILT
System architecture
ACCIMT · Space Applications Division
3
External sources
e-CALLISTO FITS archive, ACCIMT Sri Lanka prioritised
NOAA SWPC: GOES X-ray, proton, electron, magnetometer
SDO/AIA, HMI and GOES/SUVI full-disk imagery
SOHO/LASCO C2 and C3 coronagraph frames
Kyoto WDC Dst, planetary Kp, F10.7, sunspot number
Backend — FastAPI
14 scheduled collectors (APScheduler, UTC throughout)
FITS loading, RFI cleaning, background subtraction
Burst, event and shock detection modules
Native PyTorch inference (ResNet-18 classifiers)
13 REST route groups, OpenAPI documented
Storage & cache
PostgreSQL + TimescaleDB hypertables for time series
Redis cache in front of live fetches and DB reads
Large products (FITS, spectra, images) kept on disk
Metadata and file paths held in the database
Alembic migrations — 11 applied to date
Frontend — Next.js 14
TypeScript, Tailwind CSS and Plotly.js
18 pages: overview, radio, analyzer, imaging
Forecast, timeline, archive and settings
SWR polling keeps live panels current
Light and dark themes, responsive layout
Deployed as four Docker Compose services — frontend, backend, PostgreSQL/TimescaleDB, Redis — so the whole stack starts with a single command on the observatory machine.
Notes: Collect once on a schedule, store in TimescaleDB, serve through Redis, and fall back to a live fetch only when the database has a gap.

## Slide 4
DELIVERABLE · COMMON INTERFACE
The monitoring dashboard
ACCIMT · Space Applications Division
4
[ screenshot: overview.png ]
Overview — single-screen status of the Sun and near-Earth space, all times in UTC.
1
Live at a glance
X-ray class, >10 MeV proton flux, Kp, Dst, solar wind and active alerts in one strip, refreshed automatically.
2
Live dynamic spectrum
The ACCIMT / Sri Lanka CALLISTO feed rendered continuously, with detected bursts pinned on the spectrum.
3
Everything else one click away
18 pages covering radio, imaging, coronagraph, geomagnetic, forecast, timeline and archive.
Notes: The August deliverable — a common interface monitoring dashboard — is in place and running.

## Slide 5
DELIVERABLE · JULY – SEPTEMBER
e-CALLISTO solar radio module
ACCIMT · Space Applications Division
5
[ screenshot: solar-radio.png ]
Solar Radio — dynamic spectra from the e-CALLISTO network with station selection and processing controls.
FITS files read directly from the e-CALLISTO archive, with the ACCIMT Sri Lanka station prioritised
Background subtraction and RFI cleaning applied before display
Frequency–time dynamic spectra rendered interactively (zoom, range, station compare)
Daily burst list ingested and cross-checked against detections
Analyzer page for uploaded FITS: manual burst selection, drift-rate and shock-speed analysis
Why it matters
Observations that previously required manual file handling are now viewable and reducible in the browser, by students and collaborators alike.
Notes: July's prototype web interface for CALLISTO data, extended through August and September into the full radio module.

## Slide 6
AHEAD OF SCHEDULE · PLANNED FOR NOVEMBER
AI-based burst detection and classification
ACCIMT · Space Applications Division
6
[ screenshot: burst-detector.png ]
Burst Detector — model selection, scan window and detections with confidence.
CCM v1.1.0
burst / no-burst
Test F1 0.932
CCMT v1.0.0
Type II / III / other
Accuracy 0.966
CCM v1.0.0
original baseline, kept selectable
Threshold 0.595
ResNet-18 classifiers run natively inside the backend — no separate service to keep alive
The scanner scores the live archive on a schedule; an offline catch-up fills days missed during downtime
Detections are de-duplicated per model, so a retrained model can be swapped in without losing comparability
Burst-positive segments are cropped and typed; regions outside the classifier's training distribution are left untyped rather than guessed
Notes: The November deliverable — AI classification for CALLISTO data — is already running in the dashboard. Types are reported as estimates.

## Slide 7
DELIVERABLE · OCTOBER, LARGELY IN PLACE
Multi-parameter space weather integration
ACCIMT · Space Applications Division
7
[ screenshot: timeline.png ]
Timeline — radio bursts, flares, CMEs and geomagnetic response on one axis, linked into event storylines.
Solar
GOES XRS X-ray flux with flare classes · SDO/AIA and HMI imagery · SOHO/LASCO C2 & C3 · sunspot number · F10.7
Particles
GOES proton and electron flux, multiple energy channels · magnetometer
Geospace
Planetary Kp · Dst index · solar wind speed, density and IMF Bz / Bt
Forecast
NOAA 3-day outlook and NOAA scales · predicted Kp · DONKI CME catalogue with transit estimates · aurora outlook
Events are derived from the ingested series every ten minutes and chained into storylines — flare → CME → radio burst → geomagnetic storm — with alerts and notifications on the significant ones.
Notes: October's integration deliverable — GOES X-ray, SGPS proton, Dst and Kp alongside the radio data — is substantially complete; the remaining work is tuning and continuous-operation hardening.

## Slide 8
DELIVERABLE · SEPTEMBER
Imaging and analysis tools
ACCIMT · Space Applications Division
8
[ screenshot: data-analysis.png ]
Data Analysis — multi-mission solar image analysis.
[ screenshot: analyzer.png ]
e-CALLISTO Analyzer — shock analysis on an imported spectrum.
Solar imaging
SunPy / aiapy pipeline: AIA level-1.5 preparation, HMI composites, difference imaging, multi-viewpoint reprojection and movie export.
Signal intensity
Light curves, height–time and J-map measurements taken directly off the images and spectra.
Archived datasets
Performance verified against archived observations, not only the live feed — the basis for the September prototype sign-off.
Notes: H-alpha ingestion is the piece still outstanding here — the imaging and measurement tooling it will plug into is already built.

## Slide 9
STATUS · MAY – SEPTEMBER 2026
Deliverables against the work plan
ACCIMT · Space Applications Division
9
Month
Expected deliverable
Status
May
Literature review summary
Complete
June
Requirement analysis, existing-setup documentation, system architecture
Complete
July
Prototype web interface for CALLISTO data
Complete
August
Common interface monitoring dashboard (CALLISTO + imaging)
Complete
September
Real-time monitoring prototype; imaging and intensity visualisation tools
Complete — H-alpha ingestion pending
Ahead of plan
AI burst detection and classification (scheduled for November)
Running in the dashboard
Supporting activity: astronomy and space-science workshops and night-sky observation programmes conducted as scheduled by the division.
Notes: Five monthly deliverables complete. September is complete apart from H-alpha data ingestion, which depends on access to the H-alpha system's output.

## Slide 10
OCTOBER – DECEMBER 2026
Future work
1
H-alpha integration
Ingest the H-alpha imaging output and place it alongside the radio spectra on the common interface, completing the multi-wavelength view.
2
Simultaneous detection
Couple the AI burst detector to the space weather parameters so a radio burst, its flare and its CME are confirmed against each other automatically.
3
Continuous operation
Harden the stack for unattended running: retention policy, restart recovery, source-health alerting and performance tuning under a full archive.
4
Model improvement
Retrain on locally observed ACCIMT events, extend typing beyond Type II / III, and report calibrated confidence.
5
Documentation & handover
Complete architecture, API and data-source documentation, operator guide, and deployment notes for the observatory machine.
6
e-CALLISTO network link
Prepare the station's data path for routine contribution to the global e-CALLISTO archive.
Target: a fully functional CALLISTO observation platform with multi-parameter space weather integration, documented end to end, by 31 December 2026.
Notes: Closing slide — the December target from the work plan, and the six workstreams that get there.